## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | TESDA-MIS. OCC
PROCUREMENT MONITORING REPORT FOR THE 2nd SEMESTER (July - December 2018 2018)
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Eval. | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
A. COMMON USE SUPPLIES AND EQUIPMENT (AVAILABLE AT PROCUREMENT SERVICE)
A.1 Common electrical Supplies
| A.2 Common Office Supplies | [19 empty] | TESDA-MOCC | Agency-to-Agency | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7.3.2018 | 7.3.2018 | N/A | 7.3.2018 | 7.3.2018 | GoP | 1570.5 | 1570.5 |  | 1739.64 | 1739.64 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | 52.1b (Shopping) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7.18.2018 | 7.18.2018 | N/A | 7.18.2018 | 7.18.2018 | GoP | 1413.5 | 1413.5 |  | 1413.5 | 1413.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | 52.1b (Shopping) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10.25.2018 | 10.29.2018 | N/A | 10.29.2018 | 10.29.2018 | GoP | 3340 | 3340 |  | 3218.6 | 3218.6 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A. 3 Common Office Divices
A.4 Common Janitorial Supplies
A.5 Common Office Equipment
A.6 Handbook on Procurement
A. 7 Consumables
B. OTHER ITEMS NOT AVAILABLE AT PS BUT REGULARLY PURCHASED FROM OTHER
| B.1 Common Electrical Supplies | [19 empty] | TESDA-MOCC | Small Value Procurement | N/A | N/A | N/A | N/A | 2018-06-21 | N/A | N/A | 6.29.2018 | 7.4.2018 | N/A | 7.16.2018 | 7.16.2018 | GOP | 12800 | 12800 |  | 9204 | 9204 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | Small Value Procurement | N/A | N/A | N/A | N/A | 2018-06-21 | N/A | N/A | 6.29.2018 | 7.4.2018 | N/A | 7.16.2018 | 7.16.2018 | GOP | 1830 | 1830 |  | 866 | 866 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | Small Value Procurement | N/A | N/A | N/A | N/A | 2018-06-21 | N/A | N/A | 6.29.2018 | 7.4.2018 | N/A | 7.16.2018 | 7.16.2018 | GOP | 2250 | 2250 |  | 1800 | 1800 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B.2 Common Computer Supplies
| B.3 Common Office Equipment | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement
| B. 4 Common Office Supplies | [19 empty] | TESDA-MOCC | 52.1b (Shopping) | N/A | N/A | N/A | N/A | 8.15.2018 | N/A | N/A | 8.23.2018 | 8.23.2018 | N/A | 9.4.2018 | 9.4.2018 | GoP | 7028 | 7028 |  | 7028 | 7028 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | 52.1b (Shopping) | N/A | N/A | N/A | N/A | 10.25.2018 | N/A | N/A | 10.26.2018 | 11.5.2018 | N/A | 11.5.2018 | 11.5.2018 | GoP | 8883 | 8883 |  | 8883 | 8883 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | 52.1b (Shopping) | N/A | N/A | N/A | N/A | 10.25.2018 | N/A | N/A | 10.26.2018 | 11.5.2018 | N/A | 11.5.2018 | 11.5.2018 | GoP | 7030 | 7030 |  | 7030 | 7030 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[21 empty] | TESDA-MOCC | 52.1b (Shopping) | N/A | N/A | N/A | N/A | 11.21.2018 | N/A | N/A | 11.22.2018 | 11.26.2018 | N/A | 12.17.2018 | 12.17.2018 | GoP | 45000 | 45000 |  | 40500 | 40500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| B.5 Common Office Devices | [20 empty] | 52.1b (Shopping)
| B.6 Common Janitorial Supplies | [20 empty] | 52.1b (Shopping)
| B.7 Consumables | [20 empty] | 52.1b (Shopping)
| B.8 Office Equipment and Accessories | [20 empty] | 52.1b (Shopping)
| B.9 Office Supplies | [20 empty] | 52.1b (Shopping)
| B.10 Audio and Visual Presentations & Composing Equipment | [20 empty] | NP- 53.9 Small Value Procurement
| B.11 Photographic or Filming or Video Equipment | [20 empty] | NP- 53.9 Small Value Procurement
| B.12 Cleaning Equipment and Supplies | [20 empty] | NP- 53.9 Small Value Procurement
| B.13 Paper Materials and Products | [20 empty] | NP- 53.9 Small Value Procurement
| B.14 Lighting and Fixtures and Accessories | [20 empty] | NP- 53.9 Small Value Procurement
| B.15 Electrical Equipment and Components and Supplies | [20 empty] | NP- 53.9 Small Value Procurement
| B.16 Computer Supplies | [20 empty] | NP- 53.9 Small Value Procurement
| B.17 Computer Equipment and Accessories | [20 empty] | NP- 53.9 Small Value Procurement
| B.18 Vehicle Maintenance Supplies and Materials | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 11.21.2018 | N/A | N/A | 11.22.2018 | 11.27.2018 | N/A | 12.4.2018 | 12.4.2018 | GoP | 14560 | 14560 |  | 14560 | 14560 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| B.19 Publications | [20 empty] | NP- 53.9 Small Value Procurement
C. OTHERS
| C.1 Communications | [20 empty] | Direct Contracting
| C.1.1 Landline | [20 empty] | Direct Contracting
| C.1.2 Mobile (Postpaid) | [20 empty] | NP- 53.9 Small Value Procurement
| C.1.3 Mobile (Pre-paid) | [20 empty] | Direct Contracting
| C.1.4 Postage and Courrier Services | [20 empty] | Direct Contracting
| C.2 Power Consumption | [20 empty] | Direct Contracting
| C. 3 Water Utilities | [20 empty] | NP- 53.9 Small Value Procurement
| C. 4 Water Utilities (Purified Drinking Water) | [20 empty] | NP- 53.5 Agency to Agency
| C.5 Printing Services (Accountable Forms) | [20 empty] | NP- 53.9 Small Value Procurement
| C.6 Printing Services (Brochures, Newsletter, Publication, Tarpulin, etc.) | [20 empty] | NP- 53.9 Small Value Procurement
| C.7 Tokens and Other Corporate Give Aways | [20 empty] | NP- 53.9 Small Value Procurement
| C.8 Catering Services | [20 empty] | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 8.7.2018 | N/A | N/A | 8.7.2018 | 8.7.2018 | N/A | 8.10.2018 | 8.10.2018 | GOP | 37500 | 37500 |  | 30000 | 30000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[23 empty] | N/A | N/A | N/A | N/A | 8.23.2018 | N/A | N/A | 8.24.2018 | 8.24.2018 | N/A | 8.29.2018 | 8.29.2018 | GOP | 44000 | 44000 |  | 39000 | 39000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
[23 empty] | N/A | N/A | N/A | N/A | 9.19.2018 | N/A | N/A | 9.19.2018 | 9.19.2018 | N/A | 9.21.2018 | 9.21.2018 | GOP | 7750 | 7750 |  | 7750 | 7750 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C.9 Events Management (Conventions/Seminars, etc. to be held at the Hotel) | [20 empty] | NP- 53.10 Lease of Venue
| C.10 Website Hosting | [20 empty] | NP- 53.9 Small Value Procurement
C.11 Subscription
| C.11.1 Newspapers/Magazine | [20 empty] | NP- 53.9 Small Value Procurement
| C.11.1 Cable | [20 empty] | Direct Contracting
| C.12 Miscellaneous | [20 empty] | NP- 53.9 Small Value Procurement
| C.13 Furnitures and Fixtures | [20 empty] | NP- 53.9 Small Value Procurement
| C.14 Security Services | [20 empty] | Competitive Bidding
| C.15 Labor Services | [20 empty] | NP- 53.9 Small Value Procurement
| C.16 Transportation Services | [20 empty] | NP- 53.9 Small Value Procurement
| C.17 Hotel Services | [20 empty] | NP- 53.9 Small Value Procurement
C.18 Preventive Repair and Maintenance
| C.18.1 Building Supplies and Materials for repair & maintenance | [20 empty] | NP- 53.9 Small Value Procurement
| C.18.2 Furniture & Fixtures Supplies and Materials for repair & maintenance | [20 empty] | NP- 53.9 Small Value Procurement
| C.18.3 ICT Equipment Supplies and Materials for repair and maintenance | [20 empty] | NP- 53.9 Small Value Procurement
C.19 LGU Bukidnon Training Center
| C.19.1 Vehicle | [20 empty] | Competitive Bidding
| C.19.2 Tools and Equipments | [20 empty] | Competitive Bidding
| C. 20. Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 2018-09-29 | N/A | N/A | 10.8.2018 | 10.12.2018 | N/A | 10.12.2018 | 10.17.2018 | GoP | 10543 | 10543 |  | 6195.55 | 6195.55 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.1 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 2018-09-29 | N/A | N/A | 10.8.2018 | 10.12.2018 | N/A | 10.12.2018 | 10.17.2018 | GoP | 11668 | 11668 |  | 7105.75 | 7105.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.2 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 2018-09-29 | N/A | N/A | 10.8.2018 | 10.12.2018 | N/A | 10.12.2018 | 10.17.2018 | GoP | 10218 | 10218 |  | 7920.55 | 7920.55 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.3 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 2018-09-29 | N/A | N/A | 10.8.2018 | 10.12.2018 | N/A | 10.12.2018 | 10.17.2018 | GoP | 7250 | 7250 |  | 5606 | 5606 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.4 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 2018-09-29 | N/A | N/A | 10.8.2018 | 10.12.2018 | N/A | 10.12.2018 | 10.17.2018 | GoP | 7925 | 7925 |  | 4876.8 | 4876.8 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.5 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 2018-09-29 | N/A | N/A | 10.8.2018 | 11.5.2018 | N/A | 11.5.2018 | 11.5.2018 | GoP | 11475 | 11475 |  | 4217 | 4217 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.6 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 2018-09-29 | N/A | N/A | 10.8.2018 | 11.6.2018 | N/A | 11.6.2018 | 11.6.2018 | GoP | 26250 | 26250 |  | 12144.79 | 12144.79 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.7 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 2018-09-29 | N/A | N/A | 10.8.2018 | 11.6.2018 | N/A | 11.6.2018 | 11.6.2018 | GoP | 22500 | 22500 |  | 11558.84 | 11558.84 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.8 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 10.5.2018 | N/A | N/A | 10.9.2018 | 10.12.2018 | N/A | 11.5.2018 | 11.5.2018 | GoP | 34500 | 34500 |  | 12087.63 | 12087.63 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.9 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 10.15.2018 | N/A | N/A | 10.15.2018 | 10.19.2018 | N/A | 10.19.2018 | 10.19.2018 | GoP | 4630 | 4630 |  | 4938.5 | 4938.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.10 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 10.15.2018 | N/A | N/A | 10.15.2018 | 10.19.2018 | N/A | 10.19.2018 | 10.19.2018 | GoP | 4630 | 4630 |  | 4938.5 | 4938.5 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.11 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 10.15.2018 | N/A | N/A | 10.15.2018 | 10.19.2018 | N/A | 10.19.2018 | 10.19.2018 | GoP | 21655 | 21655 |  | 8833.75 | 8833.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.12 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 10.15.2018 | N/A | N/A | 10.15.2018 | 10.19.2018 | N/A | 10.19.2018 | 10.19.2018 | GoP | 21655 | 21655 |  | 10428.75 | 10428.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.13 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 10.15.2018 | N/A | N/A | 10.15.2018 | 10.19.2018 | N/A | 10.19.2018 | 10.19.2018 | GoP | 21655 | 21655 |  | 16278.75 | 16278.75 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.14 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 10.25.2018 | N/A | N/A | 10.25.2018 | 10.29.2018 | N/A | 11.5.2019 | 11.5.2019 | GoP | 48536.04 | 48536.04 |  | 38388 | 38388 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| C. 20.15 Community Based Training | [19 empty] | TESDA-MOCC | NP- 53.9 Small Value Procurement | N/A | N/A | N/A | N/A | 11.15.2018 | N/A | N/A | 11.22.2018 | 11.26.2018 | N/A | 11.29.2018 | 11.29.2018 | GoP | 49375 | 49375 |  | 48885 | 48885 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [35 empty] | 509420.04
Total Contract Price of Procurement Actitvites Conducted | [35 empty] | 377396.9
Total Savings (Total Alloted Budget - Total Contract Price) | [35 empty] | 132023.14
0N-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities
Prepared by: | [29 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
MARY ANN M. PIT | [29 empty] | ANNABEL B. AVILA | [10 empty] | MIRALUNA N. BAJE-LOPEZ
BAC Secretariat/Supply Officer | [29 empty] | BAC Chairperson | [10 empty] | Provincial Director